ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Armenia

## Contracting authority

“Vanadzor Municipality Staff” Community Management Institution (from now on Vanadzor Municipality)

## Country background

With the financial support of the European Union, Vanadzor and Gyumri, the second and the third largest cities of Armenia, assisted by their European partner city Pila from Poland, are embarking on a process of strengthening urban governance. This will be done by creating institutional capacities to address some of the priority gaps in governance and by bringing European experience and knowledge closer to the Armenian context.

Thanks to the project, Vanadzor and Gyumri will be supported to develop Geographical Information Systems that is vital for urban planning. With a unified system for data storage and management, city managers will access the information they need immediately for making quality decisions related to infrastructure, utility systems, communication networks, spatial planning, environmental protection, etc. In developing this important system, the European experience will be sought.

Vanadzor and Gyumri municipalities will pioneer in Armenia in introducing smart public transportation solutions by establishing electronic ticket validation system and importing the first 10 environmentally friendly electric buses. This will help cities meet their commitments to reduce greenhouse gas emissions. Partner city Pila of Poland will make practical knowledge in this sphere available to Armenian counterparts.

The “Alliance for Better City Governance” Project will support the municipalities of Vanadzor and Gyumri and nearby communities to design and offer their citizens a greener environment. Upgrading waste management services is another important area of urban governance that the Project will tackle.; ‘green’ context in all aspects of city management will be promoted, businesses will be empowered and encouraged to apply circular economy approach, infrastructures for effective waste recycling will be created.  The Project’s ambitious goals will be achieved through broad stakeholder involvement and cooperation, continuous improvement of city management, vigorous and creative public education and awareness campaigns to bring about behavior change among different target groups and make them co-creators of better life in their communities.

The overall objective of the ABC.GoV is to contribute to the sustainable urban governance of the cities of Vanadzor and Gyumri, Armenia:

The project anticipates to achieve the following outcomes:

### The municipalities of Vanadzor and Gyumri design and implement urban planning, waste recycling and transportation policies in line with national and European standards.

### Users of municipal transports and waste management services have access to safe, healthy, inclusive and green services.

### The residents of Vanadzor and Gyumri are more knowledgeable and aware of adverse effects of plastic waste and fuel transportation on human health and environment, change behaviour to contribute improvement of service delivery.

### Vanadzor, Gyumri, and Piła municipal employees are more knowledgeable and skilled in urban governance and service delivery.

### The project has rigorous management, monitoring, accountability, reporting and visibility mechanisms to ensure proper implementation and high visibility of the progress.

## Current situation in the sector

Currently, municipalities in Armenia need to constantly improve their capacities, knowledge and skills to mobilize more resources to ensure efficient and quality service delivery. In the course of public administration reforms the opportunities and potential of amalgamated communities are being increased, along with challenges they encounter as newly reformed communities.

The amalgamated communities are gradually becoming competitors to the large cities. Vandazor is the third largest city of Armenia. Like other local governments, despite visible progress over years, it has been experiencing many challenges on the way of improvement of good governance, public participation, and municipal services. However, the potential competition from amalgamated communities provokes Vanadzor to further improve the efficiency and quality of municipal services. In addition, given the public demand of continuous improvement of municipal services and good governance, Vanadzor Municipality is keenly interested in further strengthening the capacities of its service provision departments, knowledge and skills of the municipal employees, get familiar with local and international best practices, leverage funding from alternative sources, and ensure broader transparency and visibility of municipal activities.

## Related programmes and other donor activities

Currently, Vanadzor Municipality has been cooperating with different international organizations – EUD, EU Black Sea CBC, GIZ, World Vision, etc. Through different project, these organizations supports the municipality to improve its administrative and financial management, make investments in municipal infrastructure.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the Vanadzor Municipality initiative is to further improve good governance, public participation, and municipal services provided by the municipality.

## Purpose

PROVISION OF LOGISTIC SERVICIS FOR EVENTS

## Results to be achieved by the contractor

Providing a comfortable working environment for the staff of the Project.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Vanadzor Municipality is interested in improving its management and capacities.

## Risks

- Early determination of the project

- Local government elections;

- Unstable political situation in the country.

# SCOPE OF THE WORK

## General

### Description of the assignment

PROVISION OF LOGISTIC SERVICIS FOR EVENTS

Service Description:

The purpose of the assignment is to provide administrative and logistical support to the ABC.GoV project team in ensuring relevant logistical conditions for successful implementation of the project activities. The tenderer should submit an application package on implementation of the following project events:

- Project Launching event

- Project Closing event

- Study tour Kapan, Armenia – plastic recycling production line

- Steering Committee meetings - Policy Task Force meetings

- Project Town-hall meetings

- Training seminar (technical) on plastic recycling

- Knowledge management workshop - Networking conference on urban development - Conference on circular economy - Environmental Classes and Seminars - GIS trainings - Knowledge contest.

Service Requirements, dates, and related work:

| Event | Estimated period | Initial location |
| --- | --- | --- |
| - Project Launching event | November 2021 | Vanadzor |
| - Project Closing event | February-March, 2024 | Gyumri |
| - Study tour in Armenia, to the get familiar with the plastic recycling production line | November-October, 2021 | Kapan |
| - Steering Committee meetings | Until March 2022 Until December 2022 Until March 2023 Until March 2024 | Vanadzor,Gyumri |
| - Project Town-hall meetings | November 2021 – March 2022 | Vanadzor, Gyumri |
| - Policy Task Force meetings | October-December, 2021 | Vanadzor, Gyumri |
| - Training seminar (technical) on plastic recycling | Until December 2021 | Gyumri |
| - Knowledge management workshop | Until February 2022 | Vanadzor |
| - Networking conference on Urban Development | October-November, 2022 | Vanadzor, Gyumri |
| - Conference on circular economy | October-November, 2023 | Vanadzor |
| - Environmental Classes and Seminars | Until 2022 April | Vanadzor, Gyumri |
| - GIS trainings | November-December 2021 | Vanadzor, Gyumri |
| - Knowledge contest | April-May, 2022 | Vanadzor, Gyumri |

### Geographical area to be covered

Armenia

### Target groups

The Vanadzor municipality services provision, program development, procurement departments and their employees.

## Specific work

| Events |  |
| --- | --- |
| - Project Launching event The ABC.GoV will organize the project launching event to familiarize stakeholders about the objectives and anticipated results of the project and make sure close coordination among the stakeholders. The EU Delegation will be consulted on and involved in all preparations for launching event (5.7.1. Launching event (sub-contract) | - Half day event - 100 participants - Contact participants based on the list and contacts provided by the project team - Sign-up sheet of participants - Photos of the events - Prepare participant folders with event materials in coordination with the project team - Ensuring accommodation for up to 15 participants - Ensuring airport pick-up and drop-off for around 5 participants - Provide relevant venue with all necessary conference equipment - Ensure availability of Zoom connection - Provide 1 coffee breaks and 1 lunch for participants - Provide all other necessary facilities and services needed for normal implementation of the event - Keep close coordination with the project team. |
| - Project Closing event The ABC.GoV will organize the project closing event. The target cities, CSOs, and experts will share the achievements of the project to more than 100 participants: local governments and CSOs. This event will be a forum for participant local governments from Armenia and different countries to form city to city partnerships for further cooperation and experience sharing. The EU Delegation will be consulted on and involved in all preparations for closing event. (5.7.2. Closing event (sub-contract) | - Half day event - 100 participants - Contact participants based on the list and contacts provided by the project team - Photos of the events - Prepare participant folders with event materials in coordination with the project team - Ensuring accommodation for up to 15 participants - Ensuring airport pick-up and drop-off for up to 10 participants - Provide relevant venue with all necessary conference equipment - Ensure availability of Zoom connection - Provide 1 coffee breaks and 1 lunch for participants - Provide all other necessary facilities and services needed for normal implementation of the event - Keep close coordination with the project team. |
| - Study tour to Kapan, Armenia – plastic recycling production line Up to 15 representatives from Gyumri and Vanadzor Municipalities will participate in the training to know how the approach works both from managerial and technological perspectives. Site visit will be made to Kapan, Armenia to see how the plastic recycling start-up enterprise works in practice. (5.7.5. Study tour in Armenia (sub-contract) (incl. hall/equipment rent, accomodation, transportation, meals, experts, etc.) | - Up to 15 participants - Event with overnight - Provide transportation – round trip - Provide food and accommodation - Provide venue for training - Sign-up sheet of participants - Photos of the events - Prepare participant folders with event materials in coordination with the project team |
| - Steering Committee meetings The ABC.GoV established a project Steering Committee (SC) as the main decision-making body, which will convene 4 meetings in the course of the project. Members of the project SC will be EUD as a main donor, Mayors, representatives of RA MTAI, RA CUD, RA CC, Lori and Shirak regional governments, CSOs as members and as observers: such as a PwD organization, a women’s right organization, representatives of management and students of educational institutions in Vanadzor and Gyumri, business/private sector representatives and youth, environmental organizations, etc. (5.7.6. Steering Committee meetings) | - 4 Steering committee meetings - Half-day events - Up to 25 participants in each meeting - Provide relevant venue with all necessary conference equipment - Sign-up sheet of participants - Ensure availability of Zoom connection - Provide reception - Keep close coordination with the project team. |
| - Policy Task Force meetings The project will form 3 Task Forces on urban development, waste management and public transportation. 11 TF meetings will be convened in total. During the 1-3 of each TF meetings, the TF members will identify and prioritize gaps in urban governance policies and procedures (general urban planning, waste management and public transportation - master plan, urban development charter, and urban development map, zoning requirements; integrated waste management plans with an accent to recycling and circular economy; local ordinances promoting the use of eco-friendly public transportation, reduction of carbon emissions). (5.7.9. Policy Task Force Meetings | - 11 task-force meeting - Half day event (each meeting) - Up to 25 participants (each meeting) - Prepare participant folders with event materials in coordination with the project team - Provide relevant venue with all necessary conference equipment - Ensure availability of Zoom connection - Provide 1 coffee breaks - Provide all other necessary facilities and services needed for normal implementation of the meetings |
| - Project Town-hall meetings 3 town-hall meetings in Vanadzor and 3 in Gyumri with a support of community based CSOs to receive input of the residents and CSO on the recommended priority policies, procedures, and tools. The town-halls will start in the second half of the project Year 1. Information on town-halls will be broadly disseminated through social media and local TV’s, and posted on the municipal info-boards and other public places. Apart from face-to-face meetings, the town-halls will be live-streamed to ensure broader participation and feedback by the residents and CSOs. It is anticipated that 200 residents in each city will be involved in town hall meetings. The TF members and experts will make presentations on the amended policies and regulations. The residents and CSO will provide their feedback in the Q&A sessions. To gather as much opinions as possible, boxes labelled “Resident Voices” will be installed in the municipalities and public places for a period of month. The voices of live-stream-participants also will be considered. (5.7.8. Town-hall meetings | - 6 town hall meetings (3 in Vanadzor and 3 in Gyumri) - Half day events (each meeting) - 200 residents (each city) - Sign-up sheet of participants - Photos of the events - Prepare participant folders with event materials in coordination with the project team - Provide relevant venue - Ensure Live-stream and availability of Zoom connection - Provide all other necessary facilities and services needed for normal implementation of the meetings |
| - Training seminar (technical) on plastic recycling Up to 10 representatives from Gyumri and Vanadzor Municipalities will participate in the training to know how the approach works both from managerial and technological perspectives. (5.7.14. Training seminar (technical) | - 1 training - Half day event - Up to 10 participants - Sign-up sheet of participants - Photos of the events - Prepare participant folders with event materials in coordination with the project team - Provide relevant venue with all necessary conference equipment - Ensure availability of Zoom connection - Provide a coffee break - Provide all other necessary facilities and services needed for normal implementation of the meetings |
| - Knowledge management workshop The ABC.GoV Vanadzor team will organize a Knowledge Management workshop. In total, 30 participants (10 per city) from target cities, experts and project team will participate in the session. Piła representatives will join on-line. In case of emergency (COVID-19 or other) the entire event will be organized online for all participants. The workshop will aim to develop a common methodology for implementation of public education and awareness activities within the frame of the project. Peer review the participants will exchange existing knowledge and skills in public education considering the specifics of their communities. Experts and trainers will exchange their knowledge and methods/tools of conducting education and awareness campaigns. As a result of the workshop, the participants will agree and draft educational seminar topics, formats and questions for knowledge contest, scenarios of PSAs, and key messages for the campaigns. (5.7.15. Knowledge management workshop | - 1 knowledge management workshop - Up to 30 participants - Sign-up sheet of participants - Photos of the events - Prepare participant folders with event materials in coordination with the project team - Provide relevant venue with all necessary conference equipment - Ensure availability of Zoom connection - Provide Lunch dinner, 2 coffee breaks - Provide transportation for 10-12 participants (Gyumri-Vanadzor-Gyumri) - Provide all other necessary facilities and services needed for normal implementation of the meetings |
| - Networking conference on Urban Development The ABC.GoV will convene regional conference on sustainable urban governance entitled: City to City: joint efforts towards sustainable urban governance. It will be held at the end of the project Year 2. The purpose of the 2-day conference is to contribute to the sustainable urban governance in project target cities through peer learning and exchanging best practices. The conference will be held in Armenia, in Vanadzor and Gyumri cities. It will consist of opening and closing plenary sessions with thematic breakout sessions in-between. The project Vanadzor team will be responsible for organizing the conference with the assistance of Gyumri and Pila project teams. The EU Delegation will be consulted on and involved in all preparations for the networking conference, particularly, on the issues such as the date, format and participants can be proposed by the project team but will be agreed with the EUD before circulation of invitations, booking of venues, and launching of procurements etc. The Conference will host more than 100 representatives from the project partner municipalities, including 30 other Armenian and Polish municipalities, urban planning and urban policy representatives from Eastern Partnership (EaP) (Georgia, Ukraine, Moldova), Central and Eastern Europe EU-member countries. This will be another opportunity for the project partner cities to get exposed to the experiences and best practices of their EU counterparts in the field of urban governance. The Conference will cover social, environmental and economic aspects of urban governance with subthemes including but not limited to: access to transportation, housing, green spaces, drinking water and sewerage system, job availability and access to green jobs, efficient waste management and recycling, reduction of greenhouse gases, air quality, climate change, participatory governance, etc. Based on the diverse practices shared during the networking conference, best practice guidebook will be published in Armenian, Polish and English and distributed to participants and stakeholders. In case of emergency (like COVID-19 and other emergency) the activities connected with travel and meetings will be conducted online, the conference format will be reviewed and the budget for those activities will be adjusted accordingly. As a result Mayors of Armenia benefit from a regional networking conference as a percentage of total number of mayors in Armenia. (5.7.3. Networking conference (sub-contract) | - One conference - 2- day event - Up to 120 participants - Sign-up sheet of participants - Photos of the events - Prepare and print participant folders with event materials in coordination with the project team - Provide relevant venue with all necessary conference equipment, including a projector. - Ensure availability of Zoom connection - Provide lunch (each day), dinner (each day), 2 coffee breaks (each day) and 1 reception - Provided lodging for up to 25 participants - Provide all other necessary facilities and services needed for normal implementation of the meetings - Provide translation services |
| - Conference on circular economy The project will promote circular economy in the project cities and will share the knowledge with the peers from other regions of Armenia. A feasibility study will be conducted to figure out the potential and feasibility of the development of circular economy in Armenia. A Conference on circular economy will be organized with participation of stakeholders (central and local governments, CSOs, educational institutions, experts, international organizations, etc.) from all marzes of Armenia. The participants will get familiar with the results of feasibility study. Participants will discuss with their peers how to adapt and apply the circular economy in their communities and regions. In case of emergency (like COVID-19 and other emergency) the activities connected with travel and meetings will be conducted online, the conference format will be reviewed and the budget for those activities will be adjusted accordingly. (5.7.18. Conference on circular economy | - One conference - Up to 60 participants - Sign-up sheet of participants - Photos of the events - Prepare participant folders with event materials in coordination with the project team - Provide relevant venue with all necessary conference equipment - Ensure availability of Zoom connection - Provide lunch, 2 coffee breaks - Provided lodging for up to 10 participants - Provide all other necessary facilities and services needed for normal implementation of the meetings |
| - 5.7.10. Environmental Classes and Seminars (in 40 schools for 80 teachers, 10 NGOs, 2000 residents, at least 90 class/seminars) Environmental education for the residents, NGOs and schoolchildren: The ABC.GoV will provide environmental education for all relevant and interested CSOs, 2,000 residents, and 4,000 schoolchildren from 40 schools, higher educational and vocational educational institutions, businesses of target cities using various formats, including seminars, open classes, training and knowledge contest. ToTs will be conducted with 80 school teachers to cascade down their knowledge to the schoolchildren. Knowledge contests on environmental issues will be conducted for the youth of Vanadzor, Gyumri, and Pila for 30 schoolchildren recommended by the trained teachers. During the community seminars the experts in environmental education, climate change, and waste management will be invited to talk to people about environmental concerns in their communities. The participants will learn what adverse effects plastic waste, greenhouse gas emissions cause for the environment and on health, how the ecosystem works, what is the role of citizens in mitigating the hazardous effects. Public information materials will be provided to the participants about carbon footprint and plastic footprint and trained how to calculate their own carbon emission and plastic disposal footprints and how to mitigate them. | - 90 seminars, - 1- day event, other seminars up to half a day - 4 Environmental Classes and Seminars 80 teachers ((20 teachers in each classes), - 86 class/seminars total number of participants – up to 6010, - Sign-up sheet of participants - Photos of the events - Preparation of other materials and translation, in coordination with the project team, - Provide technical support for the relevant class, - Ensure availability of Zoom connection - 1 coffee break - Certificate preparation and printing for 80 teachers, the content must be agreed with the project team, - Up to 6010 stickers printing, the content must be agreed with the project team. |
| - 5.7.11. GIS trainings GIS trainings for the target cities’ municipal employees to become more knowledgeable in operation of GIS and skilled in urban governance and service delivery. | - 2 courses, one in Gyumri, one in Vanadzor - 1- day event - Up to 20 participants - Sign-up sheet of participants - Photos of the events - Preparation of other materials and translation, in coordination with the project team - Provide technical support for the relevant class - Ensure availability of Zoom connection - 1 coffee break, 1 lunch - Certificate preparation and printing, the content must be agreed with the project team. |
| - 5.7.16. Knowledge contest - Knowledge contest will be organized for the schoolchildren of Vanadzor, Gyumri, Pila and neighboring communities based on what they learned about environmental protection and circular economy Knowledge contests on environmental issues will be conducted for the youth of Vanadzor, Gyumri, and Pila for 30 schoolchildren recommended by the trained teachers. | - 2 contests, one in Gyumri, one in Vanadzor - Duration of each event - 1 day, - 30 participants (10 participants online) - Sign-up sheet of participants - Photos of the events - Preparation of other materials and translation, in coordination with the project team - Certificate preparation and printing for 30 schoolchildren, the content must be agreed with the project team - Provide technical support for the relevant class - Ensure availability of Zoom connection - Lunch break for 20 participants. |

The tenderer should closely work with the project team and coordinate all activities with the team before actual implementation.

Service Description:

The purpose of the assignment is to provide administrative and logistical support to the ABC.GoV project team in ensuring relevant logistical conditions for successful implementation of the project activities. The tenderer should submit an application package on implementation of the following project events:

- Project Launching event

- Project Closing event

- Study tour Kapan, Armenia – plastic recycling production line

- Steering Committee meetings - Policy Task Force meetings

- Project Town-hall meetings

- Training seminar (technical) on plastic recycling

- Knowledge management workshop - Networking conference on urban development - Conference on circular economy - Environmental Classes and Seminars - GIS trainings - Knowledge contest.

For each route, car's delivery location is agreed with the customer in advance.

In preparing this section, focus should be placed on ensuring the sustainability and dissemination of project results. The contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

## Project management

### Responsible body

Vanadzor Municipality

### Management structure

Vanadzor Municipality will coordinate all aspects of the technical assistance through the Municipality's program development department.

# LOGISTICS AND TIMING

## Location

Armenia

## Start date & period of implementation of tasks

The intended start date is 29 october 2021 and the period of implementation of the contract will be 31 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that the Project Staff is adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable the Project Staff to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# MONITORING AND EVALUATION

## Definition of indicators

Monitoring and evaluation of the activity will be provided in accordance with the Vanadzor Municipality's policies, procedures and by the oversight of a staff member that is included in the Project team.